## Slide 1: File Build & File Maintenance for the Cannabis Industry

## Slide 2
Business Overview

## Slide 3: Business Problem:
3
Our files currently don’t reflect all the businesses that have been licensed to conduct business in the marijuana industry. We have about 2,500 businesses in file, but the 30 states that have legalized marijuana usage have over 10,000 businesses licensed to handle a variety of roles within the marijuana sector.
Customer Value Proposition:
Some customers/potential customers are looking to better prospect to the new marijuana industry utilizing our business intel
The financial sector is turning to us to figure out who they should avoid conducting business with from a compliance point of view
Additional elements include greater visibility to total risk, more foundational data to support superior predictive analytics, and continued development of SIC codes related to the field
Market Trends & Competitive Landscape:
As a market leader, we are expected to be out in front of any new industries, so addressing this need will help meet customer expectations, filling in current gaps. We are responding to customer inquiries around this area, we are not out in front of this new industry.
Given that the source of the data is public, our competitors will also be extracting this data at some point
There are about 5-10 websites that cater to this new industry, already providing data on demand. While we provide greater capability, there are start-ups that are much more nimble within this new industry
Dependencies, Assumptions & Constraints:
Our list will not represent an entire census of the licensed marijuana industry, given that some states aren’t legally permitted to release to the public all engaged businesses, for security and safety reasons
Some states provide easy access to the licensed data, while others simply post via their websites or via attachments, making automation more challenging
Discovery, curation and ingestion will rely on a cross functional team, making the project dependent upon the teams availability and support – Content Innovation, SIC Development, IE Processing, etc.
We are building functionality based on available public sources, which may lead to some future limitations if/when new sources might become available

## Slide 4
Project Scope
Notes: Saleem

## Slide 5: Project Steps
5
Role | Owner
Draft a flow chart of the processing of the public marijuana data depicting the steps required from beginning to end | Leo
Create a file layout & data dictionary of all the elements we’ll be extracting from the state sources | Leo
Plan to web scrape the several different types of data sharing the states provide Bulk sources Posted on state website Posted via state website link through an attachment Via a search tool | Leo
Share any new types of marijuana licenses/data elements that might support the development of new SIC codes with Brian McGillicuddy | Leo
Craft rules that will select one of the marijuana based SIC’s to include in the extraction file; Confirm rules based process with Brian McGillicuddy; Thinking this processing step will reside in-house after we extract the raw data. | Kevin & Brian
Include a “status” field within the extraction file, and create codes supported by the data that is made available by the states. Example, “Active”, “Inactive”, “Pending”, etc. | Leo
Change Detection - Design a way to cross reference former monthly extraction files as a way to determine if a company is no longer licensed by any state to work within the marijuana industry. This process will help remove marijuana SIC’s for companies that are no longer working within the industry. Examples would include, a company listed during the last extraction, but not appearing in the next extraction, or appearing within the file, but data that indicates the license has expired or became inactive. | Leo
Work with SIC assignment, Brian McGillicuddy, to figure out if our automated processing will trigger the removal of an inactive license, or if it will simply trigger an investigation in order to confirm the removal of the SIC. | Kevin & Brian
Route the appropriate data elements to the correct location depending upon how Brian prefers to handle such cases that require SIC adjustments | Leo
Attempt to design a way to indicate if a state has moved the location/link of where they release marijuana data. When triggered, put in steps to investigate the states sites to determine if the data is being released via another link/location, and make revisions to map to the new location | Wenbin
Design a method to direct the output files to the operational teams that will handle the processing of the scraped data | Leo
Test the extraction process, revising where needed | Leo
Compare the list of companies extracted via our processing, vs. existing companies on file with marijuana based SIC’s as a way to help validate all SIC assignments | Brain
Support the Operating team with any revisions that might be required after they process files on their end | Wenbin
Collect key stats to report on the impact the project has had | Leo
Complete the weekly project status update to report on progress and any concerns | Leo

## Slide 6: Project: Cannabis File Build/Maint. ● Weekly Status Update ● as of 5/22/18
  Inventory of 30 state sites – located the public data that is available
  Completed Data Gov. review and recommendations
  Gained approval of Data Quality Executive Sponsor – Eric Rusack
  Created project scope for Leo A., project lead
  Lined up operational owner
  Coordinated strategy around SIC development
Key Activities & Accomplishments This Month
Planned Activities & Accomplishments for next phase
Issues/Risks | Proposed mitigation/action
Transition of project to summer intern dependent upon skill level of intern | Providing Leo with guidance via Tech Support from Wenbin and Project Mgt. support from both Jenn and Kevin
Project Objectives:
Increase coverage of the cannabis industry
Improve thickness of US records
  Draft flow chart of processing steps: Think through all the steps required and depict via a flow chart
  Create a data dictionary/file layout of marijuana related elements:
Top Level Milestones and Deliverables
Foundational Work
Date TBD
Curate data
Cross Functional Implementation
Date TBD
Scrape raw data
Date TBD
Date TBD
Goal:
6
Past Due / Significant
Risk to on Time Delivery
At Risk with Remediation Plan
On Track
(In Progress)
Complete
Staged

## Slide 7
Appendix

## Slide 8: Project Management Administration
8
Version | Amendment Date | Description
V.1 | May 22, 2018 | Initial draft version
V.2 | May 23, 2018 | JS Revisions
Role | Staff
Executive Sponsors | Saleem Khan, Eric Rusack
Tech Lead | Wenbin Zhang
Business Lead | Kevin Conley
Project Lead | Leo Atkinson
Support | Jenn Strauss, Brian McGillicuddy
Operating Owner | Steph Helfrich, Rob Hauke